## Slide 1
Title
AI-Powered Project Planning & Risk Forecasting
Capstone Project | 4 Weeks | 2 Teammates
Subtitle:
From deterministic planning to probability-based decision support.

## Slide 2
Problem
• Teams commit to single-date plans without uncertainty modeling.
• Delays appear late, when mitigation is expensive.
• Stakeholders need risk-aware commitments, not only task lists.

## Slide 3
Solution
ProjectSense AI:
• Generates a structured task plan from plain-language project input.
• Validates dependencies and durations.
• Simulates timeline risk with Monte Carlo.
• Recommends safer execution scenarios.

## Slide 4
Architecture (Only What Is Needed)
Flow:
1. User project description
2. LLM task generation (or mock fallback)
3. Schema validation (Pydantic)
4. DAG + critical path
5. Monte Carlo simulation
6. Metrics + scenarios + exports
Tech:
• Streamlit, Groq, Pydantic, NetworkX, NumPy/Pandas, Plotly, SQLite

## Slide 5
Live App Walkthrough
Show the 6 tabs:
• Executive Brief
• Task Plan
• Workflow
• Risk Dashboard
• Scenario Lab
• History & Export

## Slide 6
Forecast Metrics
Explain:
• Mean completion time
• P50 (median outcome)
• P80 (recommended commitment date)
• Delay probability against selected deadline
Decision message:
Use P80 for realistic commitments under uncertainty.

## Slide 7
Risk Drivers
• Critical-path frequency ranking identifies bottleneck tasks.
• Prioritize mitigation on top-ranked drivers first.
• Result: higher schedule reliability with targeted effort.

## Slide 8
Scenario Decision Support
Three scenarios:
• Baseline
• Aggressive deadline (-15%)
• Increased capacity (+15% faster)
Explain how recommendation is selected:
lowest delay probability.

## Slide 9
Product & Engineering Quality
• Input validation and graph checks
• Session persistence with SQLite
• Exportable CSV/JSON outputs
• Smoke test + unit test suite
• CI pipeline via GitHub Actions
• Dockerized local reproducibility

## Slide 10
Team Workflow (4 Weeks)
• Week 1: scope + architecture + base app
• Week 2: analytics engine + notebook
• Week 3: scenarios + persistence + test hardening
• Week 4: CI + rehearsal + final packaging
Include DoR/DoD and ownership split between both teammates.

## Slide 11
Responsible AI (Right-Sized for Scope)
• No personal data required for this demo.
• User input transparency: generated plan is editable and reviewable.
• Risk note: LLM outputs can be imperfect; schema validation and manual review are required.
Why included:
shows practical AI governance without over-scoping the project.

## Slide 12
Results, Limits, Next Steps
Results:
• Faster planning cycle
• Earlier risk visibility
• Better commitment quality
Current limits:
• Single-project scope
• No multi-user auth/integrations
Next steps:
• Portfolio view
• Jira/Asana connectors
• Optional cloud deployment